## Sheet1
Luke Wingert Tasks (polishing + multiplayer)
Tasks: | Estimated Completion Date | Actual Completion Date | Difficulty
Fix Hitboxes | 2022-04-20 | 2022-04-23 | medium
Room Switch Bugs Hud | 2022-04-23 | 2022-04-23 | medium
Fix throwing boomerang left | 2022-04-18 | 2022-04-18 | easy
Don't allow multiple boomerangs to be thrown | 2022-04-20 | 2022-04-23 | medium
Link can use items without having them | 2022-04-21 | 2022-04-16 | hard
Link can walk through locked doors | 2022-04-18 | 2022-04-23 | easy
Link's projectiles don't go over water | 2022-04-19 | 2022-04-19 | easy
Boomerang doesn't return to player if it hits a wall | 2022-04-20 | 2022-04-19 | medium
Inconsistent movement when pressing multiple keys | 2022-04-21 |  | medium
Old man text disappeared | 2022-04-20 | 2022-04-23 | easy
Enemies clip through walls in some edge cases | 2022-04-21 | 2022-04-21 | medium
Animate the fairy item (make it heal player?) | 2022-04-21 |  | easy
Fix item pick up animations | 2022-04-21 | 2022-04-23 | medium
Allowing HUD to support two player | 2022-04-22 | 2022-04-22 | medium
Replace magic numbers, clean up code | 2022-04-23 |  | hard
Player can go through weak walls | 2022-04-19 | 2022-04-19 | easy
Player 2 boomerang returns to player 1 | 2022-04-23 | 2022-04-23 | Medium
map shows up instead of compass [test room] | 2022-04-23 | 2022-04-23 | easy
left click crash on title screen | 2022-04-23 | 2022-04-23 | easy
Refactor player projectiles to use a projectile factory | 2022-04-23 | 2022-04-23 | medium
Test room is missing a door to leave | 2022-04-24 | 2022-04-24 | easy
Add special boomerang and special arrow items | 2022-04-24 | 2022-04-24 | easy
Have item cheat controls for the grader to test stuff |  |  | medium
Implement special versions of projectiles | 2022-04-25 | 2022-04-25 | easy
Boomerang deletes itself after hitting another player | 2022-04-25 | 2022-04-25 | easy
Fix 2 player death [sound + animation | 2022-04-25 | 2022-04-25 | medium
Put in new music | 2022-04-25 | 2022-04-25 | medium
Block puzzle can be skipped if all enemies are killed |  |  | medium
Heart containers get collided with twice | 2022-04-25 | 2022-04-25 | medium
Ting Feng Tasks (multiplayer)
Tasks: | Estimated Completion Date | Actual Completion Date | Difficulty
2 Player Implementation | 2022-04-22 | 2022-04-22 | Hard
2 Player Refactoring | 2022-04-19 | 2022-04-19 | Medium
Main Menu | 2022-04-19 | 2022-04-19 | Easy
KeyboardController | 2022-04-19 | 2022-04-19 | Easy
Austin M (level change refactoring, effect for room 1)
Tasks: | Estimated Completion Date | Actual Completion Date | Difficulty
refactor room changing | 2022-04-20 | 2022-04-20 | medium
darkroom effect for room 1 | 2022-04-23 | 2022-04-22 | hard
new fade in/fade out transition type for room 1 | 2022-04-20 | 2022-04-20 | medium
make walking through door more natural | 2022-04-20 | 2022-04-19 | easy
make room transition triggers between room 1 and 2 | 2022-04-20 | 2022-04-20 | medium
Craig C (Finish the HUD/Inventory and Extra boss)
Tasks: | Estimated Completion Date | Actual Completion Date | Difficulty
Item selection in Inventory State | 2022-04-21 | 2022-04-21 | Hard
Player 2 picking up heart container doesnt add new heart | 2022-04-25 | 2022-04-25 | medium
print inventory items when picked up | 2022-04-21 | 2022-04-21 | Easy
Candle in inventory | 2022-04-25 | 2022-04-25 | medium
Implement item selection box | 2022-04-19 | 2022-04-19 | Hard
Printing selected item in B slot of HUD | 2022-04-21 | 2022-04-21 | Easy
Second health bar for 2 player | 2022-04-22 | 2022-04-24 | medium
Green dot only draws if the map exists | 2022-04-22 | 2022-04-24 | easy
Triforce location when player has compass | 2022-04-22 | 2022-04-25 | easy
fix HUD and Inventory counts when > 100 | 2022-04-24 | 2022-04-24 | easy
add room to maps | 2022-04-22 | 2022-04-22 | easy
Make start room to the left by one room | 2022-04-24 | 2022-04-24 | easy
Zening ( Extra boss)
Tasks: | Estimated Completion Date | Actual Completion Date | Difficulty
refactor enemy code(eliminate magic numbers) | 2022-04-24 | 2022-04-25 | easy
new boss:manhandla | 2022-04-22 | 2022-04-24 | hard
new movement logic for manhandla fireball | 2022-04-22 | 2022-04-24 | hard
keep fixing the hitbox issue | 2022-04-24 | 2022-04-24 | medium
fix the issues that mention in the sprint4 feedback |  | 2022-04-25 | easy
new boss room | 2022-04-19 | 2022-04-19 | easy